## 2024_2025
STATE OF TENNESSEE
FY 2024~2025 OPERATIONAL CLOSE~OPEN CALENDAR
Due Date | Task | Responsibility Of
GENERATE FY24 EDISON ZERO BUDGET
2024-06-14 | Notify F&A Budget of changes to allotment codes to be effective Jul 1 | State Agencies
2024-06-28 | Generate FY25 zero budget entries | Accounts
2024-06-30 | Begin making additions or changes to FY25 zero budget entries | Accounts
BEGINNING OF NEW FISCAL YEAR
2024-06-20 | Notify Accounts of approved changes to allotment codes that must be made by Jul 1 | F&A Budget
2024-06-20 | Requests for new FY25 chartfields that must be established by Jul 1 | State Agencies
2024-06-24 | Requests for changes/new speedcharts for FY25 that must be completed by Jul 1 | State Agencies
2024-06-24 | Agencies request to Edison new iNovah allocations for FY25 | State Agencies
2024-06-24 | Agencies request to Edison to change existing allocations to a different speedchart | State Agencies
2024-07-01 | Edison ready for input of FY25 transactions | Edison
7/1-7/2 | Edison run Speedchart update for iNovah | Edison
TRAVEL
Expense Reports
2024-06-30 | Expense reports for FY24 must be submitted by employee or proxy | State Agencies
2024-07-01 | Delete FY24 expense reports created using a TA and not submitted by Jun 30 so all TA's can be rolled to FY25 | Edison
2024-07-09 | Expense reports for FY24 approved by the HR Supervisor | State Agencies
2024-07-10 | Deny FY24 expense reports not approved by HR Supervisor | Edison
2024-07-12 | Expense reports for FY24 approved by the Fiscal Office | State Agencies
2024-07-15 | Deny FY24 expense reports not approved by Fiscal Office | Edison
Travel Authorizations
2024-07-12 | TAs submitted in FY24 for a FY25 trip must be approved for roll-over to FY25 | State Agencies
7/1-7/14 | Approved FY24 TAs not used on an expense report will be rolled to FY25 | Edison
Cash Advances
2024-06-27 | Pay back any outstanding cash advances for trip taken in FY24 or prior | State Agencies
REQUISITIONS, PURCHASE ORDERS AND DISBURSEMENTS
2024-06-28 | Requisitions to be carried forward into FY25 must be associated with a non-budgeted account | State Agencies
2024-07-02 | Last June Pcard file loaded | Edison
2024-07-01 | Begin canceling open FY24 requisitions remaining associated with a budgeted account | Edison
2024-07-01 | Begin canceling FY25 receipts for FY24 POs (if they are created) | Edison
2024-07-01 | Begin to delete any FY24 Vchrs with mismatched Acct/Budget Dates between PO and Vchr | Edison
2024-07-05 | Pcard transactions must be reconciled for Billing Date 6/30/24 | State Agencies
2024-07-10 | Record FY24 receipts against POs for FY24 received merchandise | State Agencies
2024-07-11 | Create/enter and modify AP Vouchers by 9 AM for goods/services received in FY24 | State Agencies
2024-07-19 | Close or cancel all FY24 POs that should not be rolled to FY25 by 9 AM | State Agencies
7/20-/21 | Begin PO Roll-Over to FY25 for all qualified FY24 POs | Edison
2024-07-11 | AP Vouchers greater than $2,000 approved by agency | State Agencies
2024-07-15 | AP Vouchers less than $2,000 approved by agency | State Agencies
2024-07-15 | AP Vouchers greater than $2,000 approved by Accounts | Accounts
WARRANT CANCELLATION AND REISSUES
2024-07-05 | Cutoff for Accounts receipt of cancellation and reissues from agencies | State Agencies
2024-07-10 | Warrant cancellations and reissues processed | Accounts
DEPOSITS
2024-06-30 | Deposit monies received on June 30 in time to make cutoff for deposits on June 30 | State Agencies
2024-07-09 | June batches in Inovah in close status | State Agencies
2024-07-10 | June deposits submitted in PeopleSoft | State Agencies
2024-07-12 | Deposits and related accounting recorded for all FY24 ACH and fedwire receipts | State Agencies
PREPAID GRANTS
2024-07-15 | Finalize billings/invoices for FY24 collected prepaids associated with grants (customer revenue contracts) | State Agencies
EDISON SUBMODULES
2024-07-15 | Edison submodules closed for FY24 except Customer Contract Module (revenue recognition) and automated indirect cost processing | Edison
2024-08-09 | Last day for Edison Customer Contract Module automated revenue recognition processes for FY24 for Grants and Projects | Edison
2024-08-09 | Last day for automated indirect cost processing for FY24 for Grants and Projects | Edison
GENERAL LEDGER JOURNALS
Sales Tax Payment Journals (IU)
2024-07-08 | Entry (debit side) of IU journals paying sales tax to TDOR | State Agencies
2024-07-09 | Entry (credit side) and submission of IU journals paying sales tax | TDOR
2024-07-10 | Approval by creating agencies of IU journals paying sales tax | State Agencies
2024-07-12 | Approval of IU journals paying sales tax by Accounts | Accounts
Multi-Unit Journals (MU)
2024-07-18 | Entry/approval of multi-unit MU journals into Edison | State Agencies
2024-07-19 | Approval of multi-unit MU journals by Accounts | Accounts
Accrued Liability Journals (LA)
2024-07-29 | Entry of accrued liability LA journals into Edison | State Agencies
2024-07-30 | Approval by creating agency of accrued liability LA journals | State Agencies
2024-08-02 | Approval of accrued liability LA journals by Accounts | Accounts
Inter-Unit Journals (IU)
2024-07-31 | Entry of IU journals by the creating agency | State Agencies
2024-08-02 | Entry and submission by second agency on IU journals | State Agencies
2024-08-05 | Approval by the creating agency and the second agency for IU journals | State Agencies
2024-08-07 | Approval of IU journals by Accounts | Accounts
Other Journals Affecting Projects/Grants (JV/AG/EX)
2024-08-05 | Entry of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction affecting projects/grants | State Agencies
2024-08-06 | Approval by creating agency of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction affecting projects/grants | State Agencies
2024-08-08 | Approval of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction affecting projects/grants by Accounts | Accounts
Other Journals NOT Affecting Projects/Grants (JV/AG/EX)
2024-08-22 | Entry of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction NOT affecting projects/grants | State Agencies
2024-08-23 | Approval by creating agency of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction NOT affecting projects/grants | State Agencies
2024-08-27 | Approval of miscellaneous JV/AG/EX journals to correct a previous FY24 transaction by Accounts NOT affecting projects/grants | Accounts
Accounts Receivable Against Accrued Liabilities Journals (RA)
2024-08-05 | Entry of accounts receivable against accrued liabilities RA journals | State Agencies
2024-08-06 | Approval by creating agency of accounts receivable against accrued liabilities RA journals | State Agencies
2024-08-09 | Accounts receivable against accrued liabilities RA journals approved by Accounts | Accounts
Accounts Receivable Not Against Accrued Liabilities Journals (RA)
2024-08-21 | Entry of accounts receivable not against accrued liabilities RA journals | State Agencies
2024-08-22 | Approval by creating agency of accounts receivable not against accrued liabilities RA journals | State Agencies
2024-08-26 | Accounts receivable not against accrued liabilities RA journals by Accounts | Accounts
COST ALLOCATION PROCESSING
2024-07-22 | Cost allocation processing begins for period 12 | Edison
2024-08-12 | Cost allocation processing begins for period 991 | Edison
2024-08-28 | Cost allocation processing begins for period 992 | Edison
EDISON CLOSING
2024-07-16 | Open period 991 for FY24 | Edison
2024-07-24 | Close period 12 for FY24 | Edison
2024-08-06 | Open period 992 for FY24 | Edison
2024-08-14 | Close period 991 for FY24 | Edison
2024-08-26 | Open period 993 for FY24 | Edison
2024-08-30 | Close period 992 for FY24 | Edison