## SPI
Instructions: Input the applicable data in the highlighted cells
Data Input
Notice to Proceed Date: |  |  | Current Date:
Current contract duration in days including any modifications by Change Order: |  |  |  | 0
Current contract sum to date including any modifications by Change Order: |  |  |  | 0
Total completed and stored to date (from latest application for payment): |  |  |  | 0
This tool provides schedule monitoring through a quantitative snapshot of project delivery. The project team needs to evaluate the results of the tool relative to the updated project schedule, payments to date, and other project elements to assist in determining whether the project is meeting the schedule.
Schedule Performance Index
| a | Current Number of Days
| b | Planned Value to Date:
| c | Schedule Performance Index:
| d | Schedule Variance (%):
| e | Schedule Impact (days):
a. Current Number of Days indicates the duration to date of the project.
b. Planned Value to Date (PV) indicates the amount of work in dollars that should have been completed within the current elapsed time. Compare this amount to the total completed and stored to date.
c. The Schedule Performance Index (SPI) provides the ratio of earned value to planned value. A value less than 1.0 indicates the project is behind schedule, a value greater than 1.0 indicates the project is ahead of schedule.
d. The Schedule Variance (SV) indicates the percentage that the work is ahead or behind schedule. A negative value indicates the project is behind schedule, a positive value indicates the project is ahead of schedule.
e. Shedule Impact indicates the approzimate number of days that the project is behind or ahead of schedule. A negative value indicates the project is behind schedule, a positive value indicates the project is ahead of schedule.