## Evaluation
Contractor Evaluation - CM/GC
Instructions: This evaluation tool should be used with its supporting scoring rubric. The rubric will further define the intention and range of each particular criteria listed. An interim evaluation should be executed on all projects using this form along with providing comments and feedback to the evaluated entity. This effort allows open communications amongst the project team and provides opportunities for improvements, if needed, before the execution of the final, and documented evaluation. Each criteria will be ranked numerically and supporting comments offered. Each field is fillable and scoring is automatically tabulated and averaged below with the total average score. Please use only whole numbers, as decimals are not allowed.
Evaluation Type | CxD : Evaluation of Contractor by Designer
Choose Evaluation Phase
Evaluator Name
Evaluator Role | Designer
Evaluator Institution
Project SBC#
Project Title | Enter the Project Title from SBC-1
Evaluation Date
Evaluation Category | Comments | Excellent/Strong = 10-8
Proficient = 7-5
Weak = 4-0
1. Preconstruction Services
a. Contractor provided sound estimating practices, leadership in cost control toward a budget compliant GMP.
b. Constructability reviews and aid in design coordination were evident in buildable design documents.
c. Successful cost control measures were implemented through value engineering without detriment to quality achievement goals
d. Efficient planning and scheduling produced an on-time or early project completion
| Total: | 0
| Average: | #DIV/0!
| (25%) weighting factor x 1.25 | #DIV/0!
2. Construction: Off-Site Operations
a. Exhibited sound project management practices, timely communications, accurate reporting and documentation. Thorough cost control practices such as change order evaluation and management.
b. Timely, thorough understanding of contract document drawings/specs. Early, proactive assessment of any design discrepancies such as: scope gaps, lacking or vague details or constructability issues.
c. Evidence of fully engaged and committed executive management. Minimal, if any staff changes occurred throughout the project.
d. Timely, well-managed close-out process producing all required deliverables, warranty point of contact. Seamless commissioning activities and coordination.
| Total: | 0
| Average: | #DIV/0!
| (15%) weighting factor x 1.15 | #DIV/0!
3. Construction: Field Operations
a. Sound leadership by superintendent and field staff orchestrating on-site operations toward an on-time or early project completion. Minimal, if any staff changes throughout project.
b. Exhibited operational awareness and courtesy during construction phase. Communication and flexibility were observed during phasing, work sequencing, utility disruptions, etc.
c. Self-directed in quality control and punch list management.
d. Well managed close-out activities enabling smooth facility turnover. Efficient management and coordination of Owner installed equipment.
| Total: | 0
| Average: | #DIV/0!
| (40%) weighting factor x 1.4 | #DIV/0!
4. Professionalism
a. Responsive to Owner/Agency and project team needs
b. Worked collaboratively toward the success of the project.
c. Clear, proactive emphasis. Timely and forward thinking in decision making.
| Total: | 0
| Average: | #DIV/0!
| (10%) weighting factor x 1.10 | #DIV/0!
| Overall Total: | 0
| Overall Total Weighted Average Score: | #DIV/0!
| Maximum Overall Total Weighted Average Score: | 12.25
| Comparative Percentile: | #DIV/0!

## Rubric
Contractor Evaluation Scoring Rubric - CM/GC
1. Preconstruction Services
Excellent/Strong(10-8 points) | Proficient(7-5 points) | Weak(4-0 points)
a. Contractor was fully vested providing detailed cost estimates for decision making, exhibited leadership in cost control throughout the design phase providing a clear path toward a budget compliant GMP. | a. Contractor's involvement was noticeable mainly when approaching budget requirement deliverables. The design and budget were often conflicting, but a series of value engineering exercises causing moderate redesign achieved a budget compliant GMP. | a. The contractor was often disengaged and did little to support alignment of design to budget. The project required substantial redesign and delayed the design schedule in order to gain a budget compliant GMP.
b. Constructability reviews and input were thorough in producing coordinated, buildable design documents free from coordination issues or scope gaps in the ensuing construction phase. | b. There were minor oversights in constructability and design coordination, but no major delays or cost overruns occurred as a result of the oversights during preconstruction. | b. Constructability, scope gaps, and design coordination issues caused construction delays, numerous RFI's, and multiple disputes during the construction phase.
c. Exhibited quality control while proactively seeking input from the project team and subcontractors in proposing value engineering suggestions. | c. The quality of the project was mostly preserved, although there were instances where substantial cost reductions were needed because of cost escalations that were unforeseen from prior budget guidance. | c. The building program and project quality were often at risk causing major redesign to salvage quality expectations mainly due to poor cost guidance and lack of effort during preconstruction.
d. Incorporated sound schedule logic, efficient trade work sequencing, and sound management of the construction schedule for an on-time or early project completion. Worked well with the design team to compress the schedule and provided input to aid in the release of early bid packages to fast-track the project (if applicable). | d. Planning and scheduling during preconstruction were adequate, but there were minor missteps and oversight causing recovery planning and out of sequence work to achieve an on-time completion. The schedule was compressed, but did not fully achieve the full time benefit of overlapping the design and construction phases (if applicable). | d. Planning and scheduling during preconstruction were lacking causing considerable delays. The project did not finish on time and LD's may have been enforced on the contractor as a result.
2. Construction: Off-Site Operations
Excellent/Strong(10-8 points) | Proficient(7-5 points) | Weak(4-0 points)
a. Contractor exhibited sound project management practices, was well organized with timely communicating and reporting throughout the project. Proactive in resolving any resulting disputes through solid communication processes and documentation. Change order necessity, management, and review practices were thorough. | a. Project management practices were adequate, although there were instances where timeliness and completeness may have been lacking in communications and reporting. On occasion, change orders and disputes could have been handled more expeditiously, but no issues escalated beyond resolution or delaying the progression of work. Change order evaluation and cost review may not have always been thoroughly evaluated prior to advancing for approval. | a. Project management practices were lacking in consistency. Documentation, communication, and reporting practices lacked thoroughness and timeliness. Disputes were common and often mishandled causing tension with many or all of the project team members and may have caused delays to the point of not meeting the project schedule milestones and/or completion date. Change orders may have been forwarded on for approval with little or no prior evaluation of necessity or cost.
b. Timely, thorough understanding of contract document drawings/specs. Early, proactive assessment of any design discrepancies such as: scope gaps, lacking or vague details or constructability issues. | b. An early and complete understanding of the contract documents may have been lacking, but none or only minor issues resulted. There may have been other instances where unnecessary communication or actions resulted, but none had overall, adversarial impact. | b. Contract document familiarity was a common problem throughout project, especially early on when cost and time impacts could have been minimized. Construction operations and project team member relationships were strained or adversarial because of the lack of effort and/or understanding of the contract documents.
c. Executive management engagement was evident in the support of critical project management and field operation activities. Minimal, if any staffing changes occurred throughout the project. | c. Executive management's support was not evident, but the performance of the project manager and field supervision may have overshadowed any support discrepancies or perceived needs. Personnel changes and/or turnover occurred, but critical operations and staff continuity did not suffer as a result. | c. Executive management's support was non-existent or only at crisis points during the project. Personnel changes during the project may have caused communication gaps/delays, schedule delays, quality issues, out of sequence work, doubt in ability to complete the project, etc.
d. Construction close-out process was timely, well managed, included all required project documentation/submittals, O&M manuals/training, final inspections, implemented clearly defined warranty period process and point of contact. Commissioning phase coordination was seamless with subcontractors, manufacturers, and building operations personnel. | d. Close-out procedures may have been lacking in particular areas, but all requirements were completed. Timeliness in the delivery of all required items may not have occurred and required follow-up to gain all items, but all were delivered and complete. Commissioning phase coordination may not have gone seamless for equipment start-up, but did not cause delay in owner occupancy or operations. | d. Close-out procedures were mostly uncoordinated. Project documentation may have been questionable/lacking. May have taken multiple attempts to gain all required manuals and training, final inspections, as-built drawings. Commissioning phase coordination may have been lacking causing equipment start-up delays resulting in facility move-in and occupancy delays.
3. Construction: Field Operations
Excellent/Strong(10-8 points) | Proficient(7-5 points) | Weak(4-0 points)
a. Superintendent and other field staff exercised sound leadership in orchestrating field operations, proactive in correcting issues. Work was timely while rigorously following the schedule which met or exceeded the Owner/Agency move-in date(s). | a. Superintendent and field staff were qualified with only minor instances in operational inefficiencies and rework without negative quality or schedule impacts. The project completed on time with intervals of recovery planning to meet the critical path milestones. | a. Superintendent and field staff displayed noticeable in competencies in leadership, planning, and execution. Staff turnover contributed to the operations issues, jeopardizing the completion and quality of the project.
b. Construction operations were conducted to achieve production, but considerable thought was put into the operational impact upon others, i.e.. communication, coordinated utility shutdowns, noise disruptions, flexibility in sequencing/phasing of work to minimize impacts. | b. Construction operations were conducted, but maybe planning, communication, coordination, flexibility, disruptive work sequencing could have been improved. Overall, the contractor was sensitive and responsive to the overall operational impact, but there was room for improvement in the outcome. | b. Construction operations may have been conducted with little regard for its impact on others or their surroundings. Little or poor communication and planning may have occurred prior to disruptive operations, utility disruptions, loss or limited facility access.
c. Self-directed in implementation of quality control for materials entering jobsite and work put in place. Punch list was managed on an on-going basis preventing quality problems from lingering toward the close-out phase of the project. | c. There were occasional quality issues during the project, but all were corrected without a detrimental impact to quality. There was some evidence in the delay of rework causing a push toward the end of the project to correct all non-conforming work, but there were no delays that prevented an on-time completion. | c. Quality issues were apparent throughout the project causing major rework and may have led to complicated disputes. Punch list items were numerous and correction of these items caused quality to suffer. Quality problems may have caused delays in final completion and multiple warranty claims.
d. Close-out activities were communicated, well-managed, and timely, enabling a smooth transition at facility turnover. Owner and vendor installed materials and equipment were well coordinated within the overall construction operations. | d. Close out and turnover were timely managed, but there were instances where coordination and delivery could have been improved. | d. Construction close-out procedures did not follow a defined, well-planned process. Information, operations materials, and training were lacking causing issues and delays in major systems start-ups and commission. Lack of schedule and facility access coordination may have caused delays for the Owner and other 3rd party vendors in the installation of their systems and equipment.
4. Professionalism
Excellent/Strong(10-8 points) | Proficient(7-5 points) | Weak(4-0 points)
a. Contractor was responsive to Owner and project team needs. | a. Contractor was mostly responsive, although there were gaps in performance at times without a detrimental impact to the project team. | a. Contractor was mostly disengaged throughout the project requiring efforts from other project team members to fulfill duties and the project suffered in accordance to the overall lack of service effort.
b. Evidence was observed of the contractor's commitment to the success of the project. Displayed the ability to work collaboratively, actions not dominated by self-interests | b. There were instances of inconsistencies in the service commitment to the team and project, but none were to the extent of causing any major delays or detriment to the outcome of the project. | b. There was little evidence of a teamwork displayed throughout the project and collaboration was mostly a struggle.
c. Operations throughout the project had a clear, proactive emphasis | c. A mix or proactive and reactive actions were observed, but operations ran relatively smooth while working with the contractor. | c. Mostly reactive actions were observed throughout the project and operations suffered as a result of the lack of foresight and operational inefficiencies.
d. Exhibited timeliness and forward thinking mentality in decision making | d. Occasional delays in decision making or taking actions were observed, but none were detrimental to the outcome of the project. | d. Poor decision making and lack of planning were often observed causing disputes and delays in the project.

## Lists (hidden)
Evaluation Type | Designer | SPA
CxD : Evaluation of Contractor by Designer | 4Site Inc | APSU
CxS : Evaluation of Contractor by SPA | A2H Inc | ETSU
| Adams Craft Herz Walker Inc | MTSU
| Adkisson & Associates Architects Inc | STREAM
| Advanced Energy Engr & Design Inc | TBR
| AECOM Technical Services Inc | TTU
| Allen & Hoshall Inc | UT
American Structurepoint Inc
ANF Architects Inc
Archimania PC
Architects Weeks Ambrose McDonald Inc
Artifice LLC
Asa Engineering and Consulting Inc
Barber McMurry Architects LLC
Barge Design Solutions, Inc
Barham Cain Mynatt Inc
Bauer Askew Architecture PLLC
Beaver Engineering Inc
Bennett & Pless Inc
Billingsley / Architecture
Binkley Garcia Architecture LLC
Blankenship & Partners LLC
braganza design/GROUP
Brailsford & Dunlavey Inc
Brewer Ingram & Fuller Architects Inc
Brg3s Inc
Buford Goff & Associates
Building Systems Group Engineering, LLC
Bullock Smith & Partners Inc
Burr & Cole Consulting Engineers Inc
Campbell & Associates Inc
Canup Engineering Inc
CBRE Heery Inc
Centric Architecture
Civil & Environmental Consultants
Civil Engineering and Surveying LLC
Clark + Associates, Architects
Clevland Salmon Architect
CMArchitects PLLC
Community Tectonics Architects
Compass Commissioning & Design
Consolidated Technologies Inc dba CTI Engineers Inc
Cope Associates Inc
DBS & Associates
DePouw Engineering, LLC
Derthick Henley & Wilkerson Architects
Design House 1411
Design Innovation Architects
Designshop, pllc
DKRS Architects/Engineers
DLR Group Inc
Dollar & Ewers Architects, Inc.
Earl Swensson Associates (ESA)
Eastern Engineering Inc
Edmonds Engineering Inc
El Dorado Inc
Elizabeth Eason Architecture, LLC
Engineering Services Group Inc
EnSafe Inc
Environmental & Civil Engineering Services
Envision Advantage LLC
EOA Architects PLLC
Evans Taylor Foster Childress Architects
Facility Systems Consultants
Fisher & Arnold Inc
Fisher & Associates
Fleming Associates Architects
Franklin Associates Architects
Fulghum MacIndoe & Associates Inc
Genesis Engineering Group LLC
Gilbert McLaughlin Casella Architects (JV)
Gilbert McLaughlin Casella Architects / Hodgson Douglas Landscape Arch (JV)
Gilbert/McLaughlin/Casella Architects, PLC
Gobbell Hays Partners Inc
Goodwyn Mills Cawood
Gould Turner Group
Gresham Smith Partners
Griggs & Maloney Inc
GRW Engineers Inc.
Haizlip Studio, PLLC
Haltom Engineering
Harley Ellis Corporation w/ Hastings Architecture
Hastings Architecture
Hedstrom Design LLC
Hefferlin + Kronenberg Architects
Heibert+Ball Land Design, LLC
Hellmuth Obata & Kassabaum Inc
Henderson Engineers, Inc.
Hethcoat & Davis Inc
HFR Inc.
Hixson Consultants Inc
HNA Engineering PLLC
Hodgson and Douglas LLC
Hurst-Rosche Inc
IBI Group Architects, Engineers, Landscape Architects, A New York General Partnership
IC Thomasson Associates Inc
Innovative Engineering Services
J Holmes Architecture
Jacobs Engineering Group Inc.
James + Associates Engineers & Planners Inc
Jensen Hughes Inc
Johnson + Associates Architects
Johnson Architecture Inc
Johnson Johnson Crabtree Architects PC
JPD Consulting LLC
JV - J Holmes Architecture/Lyle Cook Martin
Kaatz Binkley Jones Morris Architects
Ken Ross, Architect, Professional Corporation
Kimley-Horn & Associates Inc
Kline Swinney Associates
KSI Structural Engineers
Kurzynske & Associates
Latta Technical Services, Inc.
Lindsay & Maples Architects
Logan Patri Engineering
Lord Aeck & Sargent Inc
Lose & Associates Inc
Lose & Associates Inc dba Lose Design
LRK, Inc
Lyle Cook Martin Architects Inc
M Arthur Gensler Jr & Associates
M Shanks Architects
Mafett Engineering, LLC
Maffett Loftis Engineering
March Adams & Associates
MBI Companies, Inc
McCarty Holsaple McCarty Inc
McFarlin Huitt Panvini Inc
McGahey Associates Architects
McGehee Nicholson Burke Architects
Melvin Gill & Associates, Architects
Moody Nolan Inc
OGCB Inc
Olert Engineering Inc
Oliver Little Gipson Engineering Inc
Orchard Hiltz & McCliment inc dba OHM Advisors
PDS America
Pickering Firm Inc
Populous Inc
Professional Engineers Inc
Professional Environmental Consulting Inc
Quantum Environmental & Engineering Services, LLC
Red Chair Architects
Reedy & Sykes Architecture and Design
Renaissance Group Inc
Richard C Rinks & Associates Inc
Ricondo & Associates Inc
Rodney L. Wilson Consulting
Roof Design & Consulting Services Inc
Ross Bryan Associates Inc
Ross Witt PLLC
Ross/Fowler PC
Rosser International Inc
Rufus Johnson Associates
S&ME Inc
Sanders Pace Architecture
Scott Wilson Architect, LLC
Security Risk Mgmt Consultants
Self Tucker Architects
Shaw & Shanks Architects PC
Sizemore Group
Smee Busby Architects / I C Thomasson Associates, PLLC
Smee Busby Architects, PC
Smith Seckman Reid Inc
Sparkman & Associates Architects
Spirit Architecture Group LLC
Stantec Consulting Services
Studio Four Design Inc
Support Architecture LLC
Terracon Consultants Inc
The Architect Workshop PLLC
The Horrell Group Architects
The Lewis Group Architects Inc
The Orcutt/Winslow Limited Liability Limited Partnership
Theatre Consultants Collaborative
Thomas & Hutton Engineering
Thomas Weems Architect
Thompson & Litton, Inc dba BLS Thompson & Litton
Tinker Ma
TLM & Associates, Inc.
TMPartners PLLC
TriAD Environmental Consultants Inc
Tuck Hinton Architects
TWH Architects Inc
Upland Design Group Inc
UrbanARCH Associates
Vaughan Associates Architects Inc
Vreeland Engineers Inc
W&A Engineering
West Welch Reed Engineers Inc
Win Engineering LLC
WM Whitaker and Associates
Wold HFR Design
Wood Environment & Infrastructure Solution Inc
Workshop Architecture
Wystwynd Designs Inc